## Sheet1
Sl. No. | Requirements | Remarks by MGT | Remarks by AMTDC | Remarks by AmiT | Date |  | Priority | Completed for AGI version # | MGT & AMTDC REMARKS
46 | What is the point of upload signal processing path ? it is already getting uploaded from Signal processing module. |  | Explained, button is required | Attachment of signal processing files (1 or more) will be provided for each System document. | 2020-02-15 | Input received | Must have |  | 1. Upload signals in to Data base(MGT Server) in local or Cloud 2. This points is as good as how images are getting uploaded in the present version |  | 12:00 | 6:00
84 | If possible , information of first Sdoc can appear here to have some idea what is inside the system document. | After discussion with Dr. Pradeep |  | This feature is not released with AGI V2. Complex requirement and additional effort to be incurred. | 2020-02-15 | deferred | Good to have |  | This is optional
The information of first system documents should appear in front of corresponding Drill down to give more information to user.
94 | Dresser Speed (rpm) parameter to be entered here , which will help in calculating Dresser Speed(mps) which intern will be used to calculate the crush ratio Dresser Dia(mm) parameter to be added here | Dr. Pradeep will share the calculations |  | Crush ratio details are not shared yet. Mr.Pradeep to share inputs on this. | 2020-02-15 | Input not received | Must have |  | 1. This is a caculation update. 2. Already the wheel speed and crush ratio parameters are available. 3. Dresser Dia to be added in Consumables tab. 4. Dresser speed (mps) to be added in Operational Parameters tab 5. Dresser speed (RPM) already available | Formula: Crush Ratio = Dresser Speed(mps)/Wheel Speed(mps) Dresser Speed(mps)=Pi*DresserDia*DresserSpeed(RPM)/60000 | 8:00
108 | Can some text appear for each item in Drop down menu? as item changes new description of item can appear. | Dr. Pradeep will discuss with Mr. Sridhar Pai Sir and confirm after that. |  | This is complex requirement, Display recommendations for each drop down values is complex requirement to implement. Currently not in the scope of V2 as additional effort to be approved. | 2020-02-15 | deferred | Good to have |  | 1. We will write it in recommendations. 2. Feature not required.
115 | System Document Lock | System document to be locked/Freezed once user has saved the document. Once it is locked , it can be unlocked only by admin. User should still be able to Save as new System Document, and look at the system document. Only edit option will not be available for it. An extra column can appear in Application Toolkit to show if a system document is locked or Unlocked. |  | Stll checking feasibility of implementaion of requirement. | 2020-02-15 | Pending | Must have |  | 1. One more parameter - Status to be added in Derived Parameters Tab - dropdown menu with Locked and Unlocked options 2. This should be saved in the database. 3. There should be a check of this variable when the user clicks the Edit and Delete buton 4. If the status parameter is "locked" the buttons should not work and throw a popup saying the system document is locked. 5. If the status is unlocked, it can work normally. 6. The admin option to unlock to be made similar to Delete SDoc feature already available |  | 16:00 | 6:00
122 | If the user selects one parameter from a category - all the remaining parameters should be automatically loaded from the database | Details in next tab |  | Not feasible in this version of AGI. Can be talen up in next version. | 2020-02-15 | deferred | Must have |  | 1. There should be a new parameter Template which is a check box. 2. The system document with template checked should be saved as SDoc000000 and incremented with sub categories. 3. The user will be able to load these standard templates and edit from there |  | 16:00
123 | The output module should display only non-empty parameters
| Back End Chnges | Front End | Clarification | Done
Other Points –
1. What are the limitation of number of images that can be saved?
2. Dresser Speed unit still missing in
3. Dresser feed rate has unit in improper format
4. Crush Ratio calculation open by adding the Dresser Dia separately in the page
5. Spelling of Custom report wrong in output module
6. Make Export as ‘Excel’ in output module or can be as in Export optional 1. Excel 2. Pdf (In pdf 2 Options)
7. Calculations in derived parameters are coming wrong.
8. Report names should be saved by System Document _Default/Custom report. Right now everything is saved as AGI Report.
9. Grinding Wheel Make in Consumables was needed to be with Drop Down list
10. Coolant Concentration % Not shown
11. No limit Values are set yet; user can put any value as shown below
3. Added 'Stock on Face (mm) ' column in Operation Parameter for Face Grinding.(SI No. 8) Column empty – No textbox visible but after some more testing it appeared , is it a bug?
5. Once Drop down for OD, Face, etc appears align the heading properly. In this case ‘ Stage’. (SL No. 110). Please shift stage to left, to align properly
8. Following access levels to be given according to Username and Password. 1. Admin2. Master User 3. User 1 4. User 2 (SI No. 55) Not assigned any pages error. During assigning no user ID is shown
23. Everywhere search option to have parameter based search and Tab wise bifurcation. (SL No. 120) – Text is very large, please make it consistent with others
Ask sir is that ok? | In search field it only shows SDoc but when we start typing new parameters come. Atleast initially it should show all parameters when this is pressed
25. Displayed only top 10 values in ATK graphs. What does it mean? What point number in tracking sheet?
26. Added 'Input Component Dia-OD (mm)' parameter in workpiece , it was always available – Input component Face- (OD) was not available Please clarify
28. Introduced Derived Parameters in Output Module. – Some derived calculations are coming in scientific format. Please correct it 1.57648820997779E. Please round up these values till 5th decimal place
29. Resizable image. – Not working – Can’t drag, can’t resize
30. Calculated and operational parameters has to be modified for including face grinding. (SI No. 51)- Cycle Time Calculation
31. Again lower Target textbox are appearing for some parameters. This point was already sorted out in previous versions but again it appeared.
-- Introduced Custom name in Master Page
-- Reccomansation change
Review Feedback
-- Rename 'Signal file path' to 'Upload Signal file' in Derived Parameter
| -- Give gap between controls in Deroved Parameter |  |  | 1. I inserted 2 new parameter (Dresser Dia' & 'Dresser Speed (mps) in my DB
| -- upload icon inside the button |  |  | 2. Inserted 2 rows in 'ParameterFormulaDetails'
| -- Change the order of 'Crush ratio' and 'Dresser speed (mps)' |  |  | 3. Updated CalculateFlag in 'InputModuleParameterDetails' for 2 parameter( 'Crush Ratio' & Dresser speed(mps)')
| -- 'Dresser Dia' move under 'Dia Roll Size' |  |  | 4. '[dbo].[S_Get_InputParameterInsertUpdate]' in this Proc include 'CustomName' in 'Update' and 'View'
| -- Dresser Dia unit mm |  |  | 5. '[dbo].[S_Get_InputProcessEngineeringData]' in this proc, need only insert statement for Signal Process path insertion
| -- Cutter width unit (mm) |  |  | 6. '[dbo].[S_Get_SystemDocStatusSaveView]' in this proc, include 'UpdatedTS' & 'UpdatedBy' while update the Status of Sdoc
| -- Datetime in Unlock master (Check updated name) |  |  | 7. Need to change the order of 'Crush ratio' and 'Dresser speed(mps). (first 'Crush ratio' then 'Dresser speed (mps)
| -- Status label in Derived Parameter |  |  | 8. In Consumables 'Dresser Dia' comes after 'Dia Roll Size (mm)'
| -- Give edit option for Template Sdoc id |  |  | 9. Need to change the Datatype of 'Wheel Make'
-- For Tenplate Sdocid give 2 option when saveas click
-- In ATK change background color for Template Sdoc id
-- Change Datatype of Grinding Wheel make to Dropdown
-- Operational Parameter last row alignmeny
-- Change the position of Tooltip

## Sheet2
Sl. No. | [7 empty] | Completed for AGI version #
| Requirements | Remarks by MGT | Remarks by AMTDC | Remarks by AmiT | Date |  | Priority
46 | What is the point of upload signal processing path ? it is already getting uploaded from Signal processing module. |  | Explained, button is required | Attachment of signal processing files (1 or more) will be provided for each System document. | 2020-02-15 | Input received | Must have
84 | If possible , information of first Sdoc can appear here to have some idea what is inside the system document. | After discussion with Dr. Pradeep |  | This feature is not released with AGI V2. Complex requirement and additional effort to be incurred. | 2020-02-15 | deferred | Good to have
The information of first system documents should appear in front of corresponding Drill down to give more information to user.
94 | Dresser Speed (rpm) parameter to be entered here , which will help in calculating Dresser Speed(mps) which intern will be used to calculate the crush ratio Dresser Dia(mm) parameter to be added here | Dr. Pradeep will share the calculations |  | Crush ratio details are not shared yet. Mr.Pradeep to share inputs on this. | 2020-02-15 | Input not received | Must have
108 | Can some text appear for each item in Drop down menu? as item changes new description of item can appear. | Dr. Pradeep will discuss with Mr. Sridhar Pai Sir and confirm after that. |  | This is complex requirement, Display recommendations for each drop down values is complex requirement to implement. Currently not in the scope of V2 as additional effort to be approved. | 2020-02-15 | deferred | Good to have
115 | System Document Lock | System document to be locked/Freezed once user has saved the document. Once it is locked , it can be unlocked only by admin. User should still be able to Save as new System Document, and look at the system document. Only edit option will not be available for it. An extra column can appear in Application Toolkit to show if a system document is locked or Unlocked. |  | Stll checking feasibility of implementaion of requirement. | 2020-02-15 | Pending | Must have
122 | If the user selects one parameter from a category - all the remaining parameters should be automatically loaded from the database | Details in next tab |  | Not feasible in this version of AGI. Can be talen up in next version. | 2020-02-15 | deferred | Must have